## Overview
FINNest — BUILD PROGRESS
Metric | Value
Verified V1 features | 0 / 140
V1 feature progress | 0%
Verified daily tasks | 2 / 85
Last synchronized (UTC) | 2026-10-11 10:01 UTC
Source | GitHub Issues + approved status labels
Only closed issues with the verified label are checked. Closed alone is Needs Review.

## Features
FINNEST / FEATURES
Generated from verified GitHub Issues. Do not edit: changes will be replaced at the next sync.
Done | ID | Release | Category | Feature | Priority | Target Day | Status | Acceptance criteria | Owner | GitHub Issue
☐ | FIN-001 | V1 | Discovery & product | Define persona and measurable problem | P0 | 1 | Planned | Signed-off V1 product brief with exclusions and success metrics | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/2
☐ | FIN-002 | V1 | Discovery & product | Customer discovery interviews | P0 | 1 | Planned | At least 10 interviews summarized with evidence and insights | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/3
☐ | FIN-003 | V1 | Discovery & product | CA workflow discovery | P0 | 1 | Planned | At least two professional workflow interviews documented | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/4
☐ | FIN-004 | V1 | Discovery & product | Competitor and pricing research | P0 | 1 | Planned | Comparison and tested price hypotheses recorded | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/5
☐ | FIN-005 | V1 | Discovery & product | Brand configuration and rename policy | P0 | 1 | Planned | Display name comes only from config and rebrand guide exists | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/6
☐ | FIN-006 | V1 | Discovery & product | Landing page and waitlist | P0 | 1 | Planned | Privacy-conscious waitlist and signup flow works | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/7
☐ | FIN-007 | V1 | Discovery & product | Product acceptance criteria | P0 | 1 | Planned | V1 functions have explicit pass/fail conditions | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/8
☐ | FIN-008 | V1 | Discovery & product | Risk register and decision log | P0 | 1 | Planned | Major assumptions and risks have owners and follow-ups | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/9
☐ | FIN-009 | V1 | Identity & onboarding | Secure sign-up and login | P0 | 8 | Planned | Signup, login and logout tested end to end | Unassigned
☐ | FIN-010 | V1 | Identity & onboarding | Verified email onboarding | P0 | 8 | Planned | User email verification works | Unassigned
☐ | FIN-011 | V1 | Identity & onboarding | Password reset and session revocation | P0 | 8 | Planned | Reset and revoked sessions cannot access accounts | Unassigned
☐ | FIN-012 | V1 | Identity & onboarding | Financial account profile | P0 | 8 | Planned | User can create and manage owned bank/card account metadata | Unassigned
☐ | FIN-013 | V1 | Identity & onboarding | Income-type onboarding | P0 | 8 | Planned | Salary, freelance, investment and other income types selected | Unassigned
☐ | FIN-014 | V1 | Identity & onboarding | Preferences and reporting timezone | P0 | 8 | Planned | Reporting window and timezone persisted correctly | Unassigned
☐ | FIN-015 | V1 | Identity & onboarding | Sensitive session management | P0 | 8 | Planned | Expired/revoked sessions are rejected server-side | Unassigned
☐ | FIN-016 | V1 | Identity & onboarding | Onboarding tutorial and empty states | P0 | 8 | Planned | No-data users see correct next steps, not fake numbers | Unassigned
☐ | FIN-017 | V1 | Import & document ingestion | CSV import with column mapping | P0 | 14 | Planned | Supported CSV imports with preview and schema checks | Unassigned
☐ | FIN-018 | V1 | Import & document ingestion | Money amount and debit-credit normalization | P0 | 14 | Planned | Negative/positive and debit/credit variants normalized | Unassigned
☐ | FIN-019 | V1 | Import & document ingestion | Date parsing and timezone semantics | P0 | 14 | Planned | Dates parsed consistently with stated date assumptions | Unassigned
☐ | FIN-020 | V1 | Import & document ingestion | Canonical statement model | P0 | 14 | Planned | Each import preserves source, period and ownership | Unassigned
☐ | FIN-021 | V1 | Import & document ingestion | Import queue and progress indicator | P0 | 14 | Planned | Async jobs show pending, success, partial failure and error | Unassigned
☐ | FIN-022 | V1 | Import & document ingestion | File type/size limits | P0 | 14 | Planned | Unsupported or oversized files rejected safely | Unassigned
☐ | FIN-023 | V1 | Import & document ingestion | Secure upload and temporary download URLs | P0 | 14 | Planned | Unauthorized users cannot read uploaded files | Unassigned
☐ | FIN-024 | V1 | Import & document ingestion | Password-protected PDFs handled safely | P0 | 14 | Planned | Password is ephemeral and never logged or stored | Unassigned
☐ | FIN-025 | V1 | Import & document ingestion | PDF parser framework | P0 | 14 | Planned | Bank-specific parser adapters run in isolated workflow | Unassigned
☐ | FIN-026 | V1 | Import & document ingestion | Supported bank PDF parser #1 | P0 | 14 | Planned | Confirmed fixture suite passes | Unassigned
☐ | FIN-027 | V1.5 | Import & document ingestion | Supported bank PDF parser #2 | P0 |  | Planned | Confirmed fixture suite passes | Unassigned
☐ | FIN-028 | V1 | Import & document ingestion | Supported card statement parser #1 | P0 | 14 | Planned | Credit-card purchases, repayments, fees and refunds classified | Unassigned
☐ | FIN-029 | V1 | Import & document ingestion | Manual import preview and confirmation | P0 | 14 | Planned | Imported rows not persisted as final without validation path | Unassigned
☐ | FIN-030 | V1 | Import & document ingestion | Unsupported format guidance | P0 | 14 | Planned | Clear fallbacks and support request available | Unassigned
☐ | FIN-031 | V1 | Import & document ingestion | Partial extraction warnings | P0 | 14 | Planned | Missing pages/rows are surfaced explicitly | Unassigned
☐ | FIN-032 | V1 | Import & document ingestion | Statement reconciliation | P0 | 14 | Planned | Where balances exist, integrity checks flag discrepancies | Unassigned
☐ | FIN-033 | V1 | Import & document ingestion | Re-import and overlap handling | P0 | 14 | Planned | Re-import does not double-count rows | Unassigned
☐ | FIN-034 | V1 | Import & document ingestion | Raw source traceability | P0 | 14 | Planned | Every transaction links to source statement reference | Unassigned
☐ | FIN-035 | V1 | Transaction data quality | Normalized transaction ledger | P0 | 19 | Planned | Decimal amount, account and source metadata stored | Unassigned
☐ | FIN-036 | V1 | Transaction data quality | Deterministic merchant recognition | P0 | 19 | Planned | Merchant rules identify common narrations | Unassigned
☐ | FIN-037 | V1 | Transaction data quality | Rules-first categorization engine | P0 | 19 | Planned | Transparent category decisions for known patterns | Unassigned
☐ | FIN-038 | V1 | Transaction data quality | User transaction editing | P0 | 19 | Planned | Manual edits persist and show audit history | Unassigned
☐ | FIN-039 | V1 | Transaction data quality | User-defined category rules | P0 | 19 | Planned | Repeated merchant fixes become scoped rules | Unassigned
☐ | FIN-040 | V1 | Transaction data quality | Internal transfer candidate matching | P0 | 19 | Planned | Own-account transfers are not counted as income/spend | Unassigned
☐ | FIN-041 | V1 | Transaction data quality | Refund and reversal detection | P0 | 19 | Planned | Refunds reverse appropriate spending without fake income | Unassigned
☐ | FIN-042 | V1 | Transaction data quality | Credit-card repayment treatment | P0 | 19 | Planned | Bank-to-card repayments don't inflate spending | Unassigned
☐ | FIN-043 | V1 | Transaction data quality | Duplicate row identification | P0 | 19 | Planned | Same rows are ignored on overlapping uploads | Unassigned
☐ | FIN-044 | V1 | Transaction data quality | Uncertain classification queue | P0 | 19 | Planned | Low-confidence classifications require user review | Unassigned
☐ | FIN-045 | V1 | Transaction data quality | Transaction classification provenance | P0 | 19 | Planned | Original text and reason/confidence retained | Unassigned
☐ | FIN-046 | V1 | Transaction data quality | Transaction correction undo | P0 | 19 | Planned | User can reverse a mistaken category edit | Unassigned
☐ | FIN-047 | V1 | Transaction data quality | Source totals mismatch handling | P0 | 19 | Planned | Reports show unreconciled data warnings | Unassigned
☐ | FIN-048 | V1 | Financial calculations & dashboard | Income and actual spending rules | P0 | 33 | Planned | Salary, refund, investments and transfer separation validated | Unassigned
☐ | FIN-049 | V1 | Financial calculations & dashboard | Month-by-month cash flow | P0 | 33 | Planned | Correct monthly inflows/outflows shown by account/period | Unassigned
☐ | FIN-050 | V1 | Financial calculations & dashboard | Investment-contribution metric | P0 | 33 | Planned | Investments tracked separately from consumption spending | Unassigned
☐ | FIN-051 | V1 | Financial calculations & dashboard | Category breakdowns | P0 | 33 | Planned | Charts match canonical transactions | Unassigned
☐ | FIN-052 | V1 | Financial calculations & dashboard | Merchant breakdowns | P0 | 33 | Planned | Merchant totals trace back to rows | Unassigned
☐ | FIN-053 | V1 | Financial calculations & dashboard | Cross-account summary | P0 | 33 | Planned | Combined view excludes internal transfer double count | Unassigned
☐ | FIN-054 | V1 | Financial calculations & dashboard | Time-period and account filters | P0 | 33 | Planned | All analytics respect selected filters | Unassigned
☐ | FIN-055 | V1 | Financial calculations & dashboard | Historical comparison | P0 | 33 | Planned | Period-on-period comparison uses comparable coverage | Unassigned
☐ | FIN-056 | V1 | Financial calculations & dashboard | Data coverage/freshness warnings | P0 | 33 | Planned | Last import and missing statement periods shown | Unassigned
☐ | FIN-057 | V1 | Financial calculations & dashboard | Transaction drill-down | P0 | 33 | Planned | Every aggregate opens supporting transactions | Unassigned
☐ | FIN-058 | V1 | Financial calculations & dashboard | Empty/partial-data behavior | P0 | 33 | Planned | Insufficient data does not generate false precision | Unassigned
☐ | FIN-059 | V1 | Personal finance insights | Recurring-charge detector | P0 | 39 | Planned | Repeated merchant-period sequences produce candidates | Unassigned
☐ | FIN-060 | V1 | Personal finance insights | Subscriptions and fixed commitments view | P0 | 39 | Planned | Recurring monthly/annual values displayed | Unassigned
☐ | FIN-061 | V1 | Personal finance insights | Potential duplicate payment alerts | P0 | 39 | Planned | Suspected duplicate charges are clearly labeled as tentative | Unassigned
☐ | FIN-062 | V1 | Personal finance insights | Unusual spending alerts | P0 | 39 | Planned | Outliers are flagged without fraud accusations | Unassigned
☐ | FIN-063 | V1.5 | Personal finance insights | Recurring price-increase alerts | P0 |  | Planned | Meaningful increase compared with prior payments detected | Unassigned
☐ | FIN-064 | V1 | Personal finance insights | Explainable savings metrics | P0 | 39 | Planned | Cash available and invested cash explicitly distinguished | Unassigned
☐ | FIN-065 | V1 | Personal finance insights | Monthly financial summary report | P0 | 39 | Planned | Monthly report produced from audited calculations | Unassigned
☐ | FIN-066 | V1.5 | Personal finance insights | Coverage-aware health components | P0 |  | Planned | Components show evidence and avoid fake overall score | Unassigned
☐ | FIN-067 | V1.5 | Personal finance insights | Upload reminder and monthly notification preferences | P0 |  | Planned | User controls reminder frequency and channel | Unassigned
☐ | FIN-068 | V1 | Ask My Money AI | Approved financial query tools | P0 | 43 | Planned | Model cannot access DB except via allowlisted functions | Unassigned
☐ | FIN-069 | V1 | Ask My Money AI | Safe question-to-tool routing | P0 | 43 | Planned | Spending, income and comparison intents map correctly | Unassigned
☐ | FIN-070 | V1 | Ask My Money AI | Financial chat interface | P0 | 43 | Planned | Users can ask questions with usable failure messages | Unassigned
☐ | FIN-071 | V1 | Ask My Money AI | Source-backed numerical answers | P0 | 43 | Planned | Every number is derived from backend and traceable | Unassigned
☐ | FIN-072 | V1 | Ask My Money AI | Privacy-minimized model prompts | P0 | 43 | Planned | PAN/account numbers and unrelated financial rows withheld | Unassigned
☐ | FIN-073 | V1 | Ask My Money AI | Prompt injection resilience | P0 | 43 | Planned | Untrusted statement texts cannot override system behavior | Unassigned
☐ | FIN-074 | V1 | Ask My Money AI | Ambiguity and missing data responses | P0 | 43 | Planned | AI acknowledges incomplete account coverage | Unassigned
☐ | FIN-075 | V1 | Ask My Money AI | AI usage limits and cost controls | P0 | 43 | Planned | Server enforces quotas and protects expensive endpoints | Unassigned
☐ | FIN-076 | V1 | Ask My Money AI | AI evaluation set | P0 | 43 | Planned | Numerical, redaction and adversarial tests pass | Unassigned
☐ | FIN-077 | V1 | Tax readiness and policy | Private tax-document vault | P0 | 51 | Planned | Documents have user ownership, permissions and tags | Unassigned
☐ | FIN-078 | V1 | Tax readiness and policy | Tax reporting period handling | P0 | 51 | Planned | Supports historic FY/AY and newer Tax Year convention | Unassigned
☐ | FIN-079 | V1 | Tax readiness and policy | Form 16 upload and metadata extraction | P0 | 51 | Planned | Extracted fields are user-reviewable with source refs | Unassigned
☐ | FIN-080 | V1 | Tax readiness and policy | AIS/TIS upload identification | P0 | 51 | Planned | User uploads and tags source files without unofficial scraping | Unassigned
☐ | FIN-081 | V1 | Tax readiness and policy | Tax document checklist | P0 | 51 | Planned | Checklist based on declared applicable income sources | Unassigned
☐ | FIN-082 | V1 | Tax readiness and policy | Tax readiness reasons and gaps | P0 | 51 | Planned | Score/status explain exactly which documents are missing | Unassigned
☐ | FIN-083 | V1 | Tax readiness and policy | Verified official tax sources catalog | P0 | 51 | Planned | Every published change links to authoritative document | Unassigned
☐ | FIN-084 | V1 | Tax readiness and policy | Versioned rule metadata store | P0 | 51 | Planned | Effective dates, publication and verification fields captured | Unassigned
☐ | FIN-085 | V1 | Tax readiness and policy | Rule review and approval workflow | P0 | 51 | Planned | Unapproved rule changes cannot affect user output | Unassigned
☐ | FIN-086 | V1 | Tax readiness and policy | Tax policy change history and rollback | P0 | 51 | Planned | Reviewer actions and older rules remain inspectable | Unassigned
☐ | FIN-087 | V1 | Tax readiness and policy | Source-linked tax knowledge viewer | P0 | 51 | Planned | Users can see applicable sourced changes by period | Unassigned
☐ | FIN-088 | V1 | Tax readiness and policy | Professional reviewer sign-off | P0 | 51 | Planned | Tax content marked verified only after qualified review | Unassigned
☐ | FIN-089 | V1 | Tax readiness and policy | Tax limitations disclosure | P0 | 51 | Planned | Tax estimates and filing not falsely advertised as available | Unassigned
☐ | FIN-090 | V1 | CA sharing pilot | Exportable CA-ready report | P0 | 57 | Planned | Annual summary plus issues/missing documents included | Unassigned
☐ | FIN-091 | V1 | CA sharing pilot | User consent before CA sharing | P0 | 57 | Planned | Explicit selected-document sharing scopes available | Unassigned
☐ | FIN-092 | V1 | CA sharing pilot | Time-limited access invite | P0 | 57 | Planned | Invitation expires and uses secure access process | Unassigned
☐ | FIN-093 | V1 | CA sharing pilot | Revoke access immediately | P0 | 57 | Planned | Revoked professional cannot fetch resources | Unassigned
☐ | FIN-094 | V1 | CA sharing pilot | CA viewer with least privilege | P0 | 57 | Planned | CA sees only authorized package content | Unassigned
☐ | FIN-095 | V1 | CA sharing pilot | Share access audit trail | P0 | 57 | Planned | User can review share and access events | Unassigned
☐ | FIN-096 | V1 | CA sharing pilot | CA identity and invite abuse controls | P0 | 57 | Planned | Invite cannot be used by unintended recipients | Unassigned
☐ | FIN-097 | V1 | Billing and monetization | Entitlement matrix | P0 | 62 | Planned | Free/Plus/Tax Pack permissions enforce server-side | Unassigned
☐ | FIN-098 | V1 | Billing and monetization | Usage-limited free plan | P0 | 62 | Planned | API rejects exceeded free allowances | Unassigned
☐ | FIN-099 | V1 | Billing and monetization | Checkout integration | P0 | 62 | Planned | Paid checkout returns to verified order status | Unassigned
☐ | FIN-100 | V1 | Billing and monetization | Signed payment webhooks | P0 | 62 | Planned | Invalid webhook signatures are rejected | Unassigned
☐ | FIN-101 | V1 | Billing and monetization | Idempotent payment event handling | P0 | 62 | Planned | Duplicate webhooks don't duplicate entitlements | Unassigned
☐ | FIN-102 | V1 | Billing and monetization | Upgrade and downgrade | P0 | 62 | Planned | User can change plan without inconsistent balances | Unassigned
☐ | FIN-103 | V1 | Billing and monetization | Refund and cancel workflow | P0 | 62 | Planned | Refund/cancellation semantics documented and tested | Unassigned
☐ | FIN-104 | V1 | Billing and monetization | Receipts/invoice information | P0 | 62 | Planned | Required payment records accessible | Unassigned
☐ | FIN-105 | V1 | Billing and monetization | Failed payment handling | P0 | 62 | Planned | Incomplete purchase never unlocks paid rights | Unassigned
☐ | FIN-106 | V1 | Billing and monetization | Pricing and paywall UX | P0 | 62 | Planned | Feature pricing understandable before payment | Unassigned
☐ | FIN-107 | V1 | Billing and monetization | Revenue and conversion telemetry | P0 | 62 | Planned | Metrics exclude sensitive user transaction content | Unassigned
☐ | FIN-108 | V1 | Security privacy compliance | Data minimization policy | P1 | 69 | Planned | Financial PII not sent to analytics/logs by default | Unassigned
☐ | FIN-109 | V1 | Security privacy compliance | Encryption in transit and at rest | P1 | 69 | Planned | Managed encryption and TLS configured | Unassigned
☐ | FIN-110 | V1 | Security privacy compliance | Fine-grained authorization | P1 | 69 | Planned | Cross-account and CA scopes verified in API tests | Unassigned
☐ | FIN-111 | V1 | Security privacy compliance | Secrets manager and key rotation approach | P1 | 69 | Planned | Secret values are never committed | Unassigned
☐ | FIN-112 | V1 | Security privacy compliance | Private storage + signed reads | P1 | 69 | Planned | No public bucket or guessable files | Unassigned
☐ | FIN-113 | V1 | Security privacy compliance | Upload malware and content checks | P1 | 69 | Planned | Suspicious files quarantined/rejected | Unassigned
☐ | FIN-114 | V1 | Security privacy compliance | Import processor isolation | P1 | 69 | Planned | Untrusted PDFs cannot execute arbitrary code | Unassigned
☐ | FIN-115 | V1 | Security privacy compliance | Privacy notice and opt-in consent | P1 | 69 | Planned | Data use documented and required consents recorded | Unassigned
☐ | FIN-116 | V1 | Security privacy compliance | Data export function | P1 | 69 | Planned | User can export own data safely | Unassigned
☐ | FIN-117 | V1 | Security privacy compliance | Deletion request function | P1 | 69 | Planned | Data removed or retained according to documented policy | Unassigned
☐ | FIN-118 | V1 | Security privacy compliance | Session/device security | P1 | 69 | Planned | Privileged sessions handled securely | Unassigned
☐ | FIN-119 | V1 | Security privacy compliance | Audit logging and retention | P1 | 69 | Planned | Sensitive operations logged without raw documents | Unassigned
☐ | FIN-120 | V1 | Security privacy compliance | Abuse prevention and throttling | P1 | 69 | Planned | Expensive AI and auth endpoints rate-limited | Unassigned
☐ | FIN-121 | V1 | Security privacy compliance | Security dependency scanning | P1 | 69 | Planned | CI scans dependencies and secrets | Unassigned
☐ | FIN-122 | V1 | Security privacy compliance | Automated backup and restore test | P1 | 69 | Planned | Restore exercise succeeds from backup | Unassigned
☐ | FIN-123 | V1 | Security privacy compliance | Incident response guide and contact | P1 | 69 | Planned | Operational roles and escalation steps documented | Unassigned
☐ | FIN-124 | V1 | Security privacy compliance | Legal/privacy review gate | P1 | 69 | Planned | External professional review before real-data release | Unassigned
☐ | FIN-125 | V1 | Security privacy compliance | External security review gate | P1 | 69 | Planned | No unresolved critical/high issues before launch | Unassigned
☐ | FIN-126 | V1 | Security privacy compliance | Third-party processor register | P1 | 69 | Planned | AI, email, hosting and payment processors documented | Unassigned
☐ | FIN-127 | V1 | Infrastructure quality operations | Modular monolith and DB migrations | P1 | 74 | Planned | APIs and migrations reproducible from clean checkout | Unassigned
☐ | FIN-128 | V1 | Infrastructure quality operations | CI test/lint/typecheck | P1 | 74 | Planned | Every PR blocks on core checks | Unassigned
☐ | FIN-129 | V1 | Infrastructure quality operations | Staging and production separation | P1 | 74 | Planned | No shared sensitive database or secrets | Unassigned
☐ | FIN-130 | V1 | Infrastructure quality operations | Background job reliability | P1 | 74 | Planned | Retries, dead-letter and error visibility working | Unassigned
☐ | FIN-131 | V1 | Infrastructure quality operations | Financial fixture regression suite | P1 | 74 | Planned | Golden expected-output fixtures included | Unassigned
☐ | FIN-132 | V1 | Infrastructure quality operations | Integration tests import-to-dashboard | P1 | 74 | Planned | Test flows run in CI | Unassigned
☐ | FIN-133 | V1 | Infrastructure quality operations | E2E smoke and billing tests | P1 | 74 | Planned | Sandbox flow validated on every release | Unassigned
☐ | FIN-134 | V1 | Infrastructure quality operations | Monitoring and error alerts | P1 | 74 | Planned | Logs and exceptions reach configured owner | Unassigned
☐ | FIN-135 | V1 | Infrastructure quality operations | Observability privacy guards | P1 | 74 | Planned | Logging fields are sanitized and sampled | Unassigned
☐ | FIN-136 | V1 | Infrastructure quality operations | Performance load tests | P1 | 74 | Planned | Upload and query p95 budgets defined and checked | Unassigned
☐ | FIN-137 | V1 | Infrastructure quality operations | Deployment rollback runbook | P1 | 74 | Planned | Rollback and DB migration safety documented | Unassigned
☐ | FIN-138 | V1 | Infrastructure quality operations | Data recovery exercise | P1 | 74 | Planned | Backups restore readable user records | Unassigned
☐ | FIN-139 | V1 | Infrastructure quality operations | Product support ticketing | P1 | 74 | Planned | Report-problem workflow hides customer financial data by default | Unassigned
☐ | FIN-140 | V1 | Infrastructure quality operations | Accessibility and mobile-responsive web | P1 | 74 | Planned | Core flows usable keyboard/mobile | Unassigned
☐ | FIN-141 | V1 | Infrastructure quality operations | Public help/FAQ and known formats list | P1 | 74 | Planned | Users see supported file formats and limitations | Unassigned
☐ | FIN-142 | V1 | Infrastructure quality operations | Release approval checklist | P1 | 74 | Planned | Launch gates tracked and blockers prevent launch | Unassigned
☐ | FIN-143 | V1 | Infrastructure quality operations | Automated GitHub feature tracking | P1 | 74 | Planned | Issues drive checklist CSV/XLSX and progress docs | Unassigned
☐ | FIN-144 | V1 | Infrastructure quality operations | Brand-rename configuration | P1 | 74 | Planned | Display name can change without changing stable IDs | Unassigned
☐ | FIN-145 | V1.5 | Expanded personal finance | Additional bank adapters | P2 |  | Planned | Most demanded banks tested with customer fixtures | Unassigned
☐ | FIN-146 | V1.5 | Expanded personal finance | More credit card formats | P2 |  | Planned | Additional supported card parsers with reconciliation | Unassigned
☐ | FIN-147 | V1.5 | Expanded personal finance | Goals and budgeting | P2 |  | Planned | Optional goals calculated from user-confirmed inputs | Unassigned
☐ | FIN-148 | V1.5 | Expanded personal finance | Manual asset and liability records | P2 |  | Planned | Cash, deposits and loans captured as manual data | Unassigned
☐ | FIN-149 | V1.5 | Expanded personal finance | Coverage-aware net-worth summary | P2 |  | Planned | Explicit inclusion/exclusion of manually entered sources | Unassigned
☐ | FIN-150 | V1.5 | Expanded personal finance | Family household view | P2 |  | Planned | Opt-in shared finances with role boundaries | Unassigned
☐ | FIN-151 | V1.5 | Expanded personal finance | Notification preference center | P2 |  | Planned | Email/app notification channel controls | Unassigned
☐ | FIN-152 | V1.5 | Expanded personal finance | Improved merchant classifier | P2 |  | Planned | User-corrected patterns used with privacy controls | Unassigned
☐ | FIN-153 | V1.5 | Expanded personal finance | Subscription reminder automation | P2 |  | Planned | Reminder schedule based on verified recurring transactions | Unassigned
☐ | FIN-154 | V1.5 | Expanded personal finance | Localization for Indian languages | P2 |  | Planned | Accessibility-checked translations for selected languages | Unassigned
☐ | FIN-155 | V2 | Advanced tax intelligence | Professionally verified tax calculation engine | P2 |  | Planned | Tax-year/regime calculation suite independently verified | Unassigned
☐ | FIN-156 | V2 | Advanced tax intelligence | Tax regime comparison | P2 |  | Planned | Applicable tax regimes compared by verified rules | Unassigned
☐ | FIN-157 | V2 | Advanced tax intelligence | Capital gains statement normalization | P2 |  | Planned | Supported broker statements normalized with traceability | Unassigned
☐ | FIN-158 | V2 | Advanced tax intelligence | Salary and other income reconciliation | P2 |  | Planned | User+CA can inspect tax-income classifications | Unassigned
☐ | FIN-159 | V2 | Advanced tax intelligence | Personalized policy relevance engine | P2 |  | Planned | Rule-change notices filtered to declared circumstances | Unassigned
☐ | FIN-160 | V2 | Advanced tax intelligence | Estimated tax payment/TDS summary | P2 |  | Planned | Tax payments and deductions shown with verified source data | Unassigned
☐ | FIN-161 | V2 | Advanced tax intelligence | Tax notices and deadline organizer | P2 |  | Planned | User-supplied notice/reminders organized safely | Unassigned
☐ | FIN-162 | V2 | Advanced tax intelligence | CA reviewer collaboration on tax issues | P2 |  | Planned | Dedicated query and resolution workflow | Unassigned
☐ | FIN-163 | V2 | Advanced tax intelligence | Historical tax position reproducibility | P2 |  | Planned | Re-run stored inputs against pinned rules versions | Unassigned
☐ | FIN-164 | V2 | CA workspace SaaS | CA practice signup and verification | P2 |  | Planned | Professional account verification process designed | Unassigned
☐ | FIN-165 | V2 | CA workspace SaaS | Firm-level staff roles | P2 |  | Planned | Firm data segregated and permissioned | Unassigned
☐ | FIN-166 | V2 | CA workspace SaaS | Client invitation and intake workflows | P2 |  | Planned | Client joins with explicit consent | Unassigned
☐ | FIN-167 | V2 | CA workspace SaaS | Document requests and reminders | P2 |  | Planned | User receives scoped requests and uploads | Unassigned
☐ | FIN-168 | V2 | CA workspace SaaS | Client readiness pipeline | P2 |  | Planned | Firm can filter missing docs and open issues | Unassigned
☐ | FIN-169 | V2 | CA workspace SaaS | Multi-client secure document dashboard | P2 |  | Planned | Professional sees only authorized clients | Unassigned
☐ | FIN-170 | V2 | CA workspace SaaS | CA comments and client review tasks | P2 |  | Planned | Threaded client-specific workflow | Unassigned
☐ | FIN-171 | V2 | CA workspace SaaS | Client tax package assembly | P2 |  | Planned | Accountant can review/edit package generation | Unassigned
☐ | FIN-172 | V2 | CA workspace SaaS | Activity and compliance audit reports | P2 |  | Planned | Firm access trails exportable to authorized admins | Unassigned
☐ | FIN-173 | V2 | CA workspace SaaS | Firm subscription tiers | P2 |  | Planned | Billing and seat/client count handled correctly | Unassigned
☐ | FIN-174 | V2 | CA workspace SaaS | Client relationship revoke/export | P2 |  | Planned | User retains control and can remove practice access | Unassigned
☐ | FIN-175 | V3+ | Future regulated integrations | Account Aggregator integration through eligible regulated arrangements | P2 |  | Planned | Consent-based bank feeds only after regulatory review | Unassigned
☐ | FIN-176 | V3+ | Future regulated integrations | Direct Income Tax ERI flow | P2 |  | Planned | Integration available only with applicable authorized status | Unassigned
☐ | FIN-177 | V3+ | Future regulated integrations | Broker API/holdings integration | P2 |  | Planned | Approved customer authorization and data sharing | Unassigned
☐ | FIN-178 | V3+ | Future regulated integrations | GST/ASP-GSP partner integrations | P2 |  | Planned | GST flows use suitable provider and consent | Unassigned
☐ | FIN-179 | V3+ | Future regulated integrations | Authorized PAN verification | P2 |  | Planned | Provider/legal access confirmed | Unassigned
☐ | FIN-180 | V3+ | Future regulated integrations | Automated financial sync scheduling | P2 |  | Planned | Only permitted integrations and revocable consent | Unassigned
☐ | FIN-181 | V3+ | Future regulated integrations | Personalized investment advice with registered providers | P2 |  | Planned | Advice offered only through properly licensed service | Unassigned
☐ | FIN-182 | V3+ | Future regulated integrations | Direct tax return submission | P2 |  | Planned | Authorized ERI and professional review path | Unassigned
☐ | FIN-183 | Future | Long-term product expansion | Family financial vault | P2 |  | Planned | Secure household document sharing and nominee records | Unassigned
☐ | FIN-184 | Future | Long-term product expansion | Freelancer invoice and expense workflows | P2 |  | Planned | Separate personal/business money context | Unassigned
☐ | FIN-185 | Future | Long-term product expansion | Sole proprietor cash flow reports | P2 |  | Planned | Tax-ready business income and expenses | Unassigned
☐ | FIN-186 | Future | Long-term product expansion | Business bookkeeping export | P2 |  | Planned | Accounting software-compatible exports | Unassigned
☐ | FIN-187 | Future | Long-term product expansion | CA marketplace discovery | P2 |  | Planned | Ethics and referral compliance reviewed before monetization | Unassigned
☐ | FIN-188 | Future | Long-term product expansion | Professional financial adviser connections | P2 |  | Planned | Registered advisers listed with clear role boundaries | Unassigned
☐ | FIN-189 | Future | Long-term product expansion | Insurance renewal/coverage organizer | P2 |  | Planned | Reminder and vault, no unlicensed product sale | Unassigned
☐ | FIN-190 | Future | Long-term product expansion | Loans and debt payoff scenarios | P2 |  | Planned | Calculators without loan origination initially | Unassigned
☐ | FIN-191 | Future | Long-term product expansion | International and multicurrency statements | P2 |  | Planned | Exchange rates and multi-entity rules validated | Unassigned
☐ | FIN-192 | Future | Long-term product expansion | Native Android and iOS | P2 |  | Planned | Mobile releases after web retention demonstrates demand | Unassigned
☐ | FIN-193 | Future | Long-term product expansion | Third-party user-authorized integrations | P2 |  | Planned | Explicit permissions and revocation | Unassigned
☐ | FIN-194 | Future | Long-term product expansion | Financial education library | P2 |  | Planned | Verified explainers with policy revision history | Unassigned

## Daily Plan
FINNEST / DAILY PLAN
Generated from verified GitHub Issues. Do not edit: changes will be replaced at the next sync.
Done | Day | ID | Week | Phase | Task | Status | Acceptance | Owner | GitHub Issue
☑ | 1 | DAY-001 | 1 | Research and requirements | Freeze V1 scope, personas and measurable success criteria | Verified Done | Reviewed work artifact or documented validation evidence | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/1
☑ | 2 | DAY-002 | 1 | Research and requirements | Interview five salaried prospective users and summarize buying pain | Verified Done | Reviewed work artifact or documented validation evidence | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/10
☐ | 3 | DAY-003 | 1 | Research and requirements | Interview five more prospects and two CAs; identify reviewer | Planned | Reviewed work artifact or documented validation evidence | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/11
☐ | 4 | DAY-004 | 1 | Research and requirements | Analyze competitors, pricing, compliance risks and name conflicts | Planned | Reviewed work artifact or documented validation evidence | Unassigned | https://github.com/Tejanshu22/PersonalFinanceManager/issues/12
☐ | 5 | DAY-005 | 1 | Research and requirements | Create user journeys, wireframes, landing page and waitlist | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 6 | DAY-006 | 2 | Architecture and secure foundations | Scaffold Next.js, FastAPI, PostgreSQL, CI and local staging | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 7 | DAY-007 | 2 | Architecture and secure foundations | Design canonical ledger, ownership, Decimal amounts and migrations | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 8 | DAY-008 | 2 | Architecture and secure foundations | Implement secure authentication and session recovery | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 9 | DAY-009 | 2 | Architecture and secure foundations | Build private file uploads, scanning and async job infrastructure | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 10 | DAY-010 | 2 | Architecture and secure foundations | Implement audit events, monitoring, environment isolation and threat model | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 11 | DAY-011 | 3 | First CSV importer | Canonical transaction/account/source data contract | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 12 | DAY-012 | 3 | First CSV importer | CSV upload with flexible column matching | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 13 | DAY-013 | 3 | First CSV importer | Normalize dates, amounts and narration safely | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 14 | DAY-014 | 3 | First CSV importer | Async import workflow with row-level error recovery | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 15 | DAY-015 | 3 | First CSV importer | Import preview and user approve/reject experience | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 16 | DAY-016 | 4 | Categorization and correctness | Deduplication and idempotent transaction imports | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 17 | DAY-017 | 4 | Categorization and correctness | Merchant normalization and classification rules | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 18 | DAY-018 | 4 | Categorization and correctness | Own-account transfer, refunds, reversals and card payment logic | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 19 | DAY-019 | 4 | Categorization and correctness | Corrections, edit history, scoped user-defined rules | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 20 | DAY-020 | 4 | Categorization and correctness | Golden fixtures and accounting edge-case tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 21 | DAY-021 | 5 | PDF and card statements | PDF framework, parser isolation, file limits and ephemeral passwords | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 22 | DAY-022 | 5 | PDF and card statements | Bank-specific PDF parser #1 with tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 23 | DAY-023 | 5 | PDF and card statements | Format variants and regression tests for first bank parser | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 24 | DAY-024 | 5 | PDF and card statements | Credit-card statement adapter with purchase/payment/refund logic | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 25 | DAY-025 | 5 | PDF and card statements | Extraction preview and reconciliation warnings | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 26 | DAY-026 | 6 | Data pipeline hardening | Bank-specific PDF parser #2 | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 27 | DAY-027 | 6 | Data pipeline hardening | Unsupported-format handling and manual fallback UX | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 28 | DAY-028 | 6 | Data pipeline hardening | Overlapping statement periods and reconciliation rules | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 29 | DAY-029 | 6 | Data pipeline hardening | Job retry, failure analytics and duplicate protection | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 30 | DAY-030 | 6 | Data pipeline hardening | Alpha test on anonymized fixtures; fix blocking parser bugs | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 31 | DAY-031 | 7 | Financial dashboard | Specify and implement income, spending and investment metrics | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 32 | DAY-032 | 7 | Financial dashboard | Category/merchant trends and reliable aggregation APIs | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 33 | DAY-033 | 7 | Financial dashboard | Build responsive dashboard with live imported data | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 34 | DAY-034 | 7 | Financial dashboard | Last-import timestamps, partial coverage labels and drill-down | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 35 | DAY-035 | 7 | Financial dashboard | Validate totals against independent calculations | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 36 | DAY-036 | 8 | Recurring intelligence | Recurring-charge detection heuristics | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 37 | DAY-037 | 8 | Recurring intelligence | Subscription and commitments dashboard | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 38 | DAY-038 | 8 | Recurring intelligence | Duplicate and unusual-spend alert candidates | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 39 | DAY-039 | 8 | Recurring intelligence | Monthly report builder with supporting details | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 40 | DAY-040 | 8 | Recurring intelligence | Health metric components with coverage restrictions | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 41 | DAY-041 | 9 | AI money assistant | Allowlisted AI financial tool interface with no arbitrary SQL | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 42 | DAY-042 | 9 | AI money assistant | Question routing and deterministic tool results | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 43 | DAY-043 | 9 | AI money assistant | AI chat UI and usage limits | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 44 | DAY-044 | 9 | AI money assistant | Source-backed answers, prompt redaction and traceability | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 45 | DAY-045 | 9 | AI money assistant | Adversarial and numeric test corpus including prompt injection | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 46 | DAY-046 | 10 | Tax-document foundation | Private tax vault and document metadata | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 47 | DAY-047 | 10 | Tax-document foundation | Historic FY/AY plus new Tax Year data model | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 48 | DAY-048 | 10 | Tax-document foundation | Form 16 upload and reviewed fields | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 49 | DAY-049 | 10 | Tax-document foundation | AIS/TIS upload workflow and document tagging | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 50 | DAY-050 | 10 | Tax-document foundation | Income-specific tax-readiness and missing-document checks | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 51 | DAY-051 | 11 | Policy and expert review | Versioned tax-rule metadata with source/effective date | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 52 | DAY-052 | 11 | Policy and expert review | Policy admin entry, review and publish workflow | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 53 | DAY-053 | 11 | Policy and expert review | Historic source linking and rule-set applicability | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 54 | DAY-054 | 11 | Policy and expert review | Audit, rollback and protected publication process | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 55 | DAY-055 | 11 | Policy and expert review | Qualified tax-expert check of supported content and examples | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 56 | DAY-056 | 12 | CA collaboration | Generate accountant-ready annual financial package | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 57 | DAY-057 | 12 | CA collaboration | Explicit limited-scope consent for CA sharing | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 58 | DAY-058 | 12 | CA collaboration | Time-limited invitation and scoped CA access | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 59 | DAY-059 | 12 | CA collaboration | Revocation, expiry and access audit tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 60 | DAY-060 | 12 | CA collaboration | End-to-end beta integration test and feature freeze | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 61 | DAY-061 | 13 | Billing | Plan and entitlements model with backend-enforced limits | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 62 | DAY-062 | 13 | Billing | Payment checkout and paid-order verification | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 63 | DAY-063 | 13 | Billing | Webhook signature checks, replay and idempotency tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 64 | DAY-064 | 13 | Billing | Refunds, failed payments, receipts and cancellations | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 65 | DAY-065 | 13 | Billing | Pricing/upgrade/paywall UX and sandbox billing rehearsal | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 66 | DAY-066 | 14 | Legal and operational hardening | Consent and privacy controls in app | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 67 | DAY-067 | 14 | Legal and operational hardening | User data exports, deletion requests and retention policies | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 68 | DAY-068 | 14 | Legal and operational hardening | Legal review of privacy, terms, cancellation and disclaimers | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 69 | DAY-069 | 14 | Legal and operational hardening | Support workflow and incident escalation | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 70 | DAY-070 | 14 | Legal and operational hardening | Automated security checks and remediation list | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 71 | DAY-071 | 15 | Release candidate | Full integration/E2E regression and authorization tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 72 | DAY-072 | 15 | Release candidate | Financial correctness and all supported format fixtures | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 73 | DAY-073 | 15 | Release candidate | Concurrency/performance and robustness tests | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 74 | DAY-074 | 15 | Release candidate | Restore backups and incident recovery rehearsal | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 75 | DAY-075 | 15 | Release candidate | Independent security assessment and fix gating | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 76 | DAY-076 | 16 | Controlled paid beta | Invite limited consenting users after release gate | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 77 | DAY-077 | 16 | Controlled paid beta | Assess import quality, corrections and user comprehension | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 78 | DAY-078 | 16 | Controlled paid beta | Test real early payments and refunds in controlled rollout | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 79 | DAY-079 | 16 | Controlled paid beta | Interview paid/free beta testers and solve biggest problems | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 80 | DAY-080 | 16 | Controlled paid beta | Document support, onboarding and production rollout | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 81 | DAY-081 | 17 | Public launch | Fix high-priority testing and feedback findings | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 82 | DAY-082 | 17 | Public launch | Final end-to-end, auth, tax-policy and billing regression | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 83 | DAY-083 | 17 | Public launch | Verify production alerts, recovery and rollback | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 84 | DAY-084 | 17 | Public launch | Full release rehearsal and go/no-go decision | Planned | Reviewed work artifact or documented validation evidence | Unassigned
☐ | 85 | DAY-085 | 17 | Public launch | Limited public launch if all security and accuracy gates pass | Planned | Reviewed work artifact or documented validation evidence | Unassigned

## How To Use
HOW AUTOMATIC CHECKMARKS WORK
STEP 1 | Create a private GitHub repo, push this starter pack and enable Issues and Actions.
STEP 2 | Create issues titled [FIN-001] ... or [DAY-001] ... using stable catalog IDs.
STEP 3 | Mark open issues in-progress or blocked when appropriate.
STEP 4 | Review the PR, passing tests, security/tax criteria and documentation.
STEP 5 | After independent verification, apply the verified label AND close the issue.
STEP 6 | GitHub Actions rebuilds the workbook, CSVs and progress documentation.
STEP 7 | A reopened verified issue is no longer checked.
RENAME | Change config/brand.json or use scripts/rebrand.py; stable IDs persist.
NOTE | The automation begins only after the GitHub repository is connected and enabled.